# Department of Family and Protective Services
Adult Protective Services
Program Performance Report
2nd Quarter FY 2011 - May 1, 2011

## Background and Summary

Senate Bill 6, passed during the 79th Texas Legislature, requires the Adult Protective Services (APS) Program to conduct a quarterly review of performance for the APS In-Home program.

The following summary provides performance information for the In-Home program for the fiscal year to date.  The rest of the report provides information and data for the second quarter of FY 2011, in the following areas:

Investigations and Service Delivery Performance – This area addresses In-Home program statewide performance indicators and benchmarks.

Highlights:  For the first six months of FY 2011, the number of intakes, the number of completed investigations and the number of investigations with an investigation are notably higher than projected benchmarks.  While workload has increased, the percentage of investigations with a confirmation is below the benchmark.

Specifically, intakes are 21.7% above the benchmarks (51,272 actual compared to 42,142 projected), completed cases are 21.7% above (42,720 compared to 35,082), the number of confirmed cases is 14.5% above (28,124 actual compared to 24,574 projected) and the percent of confirmed cases is 4.6% below (65.8% compared to 70.4%).

The average days for the investigation and service delivery are both below the benchmark.

Employee Performance – This area addresses measures and benchmarks for investigations, risk assessment and service delivery.

Highlights:  As measured through quality assurance case analysis and scoring, APS met or exceeded performance benchmarks for all investigation and service delivery stages for the quarter and fiscal year to date.

Staffing – This area addresses staffing levels and turnover rates.

Highlights:  APS caseworker turnover is continuing to increase each quarter from 3.6% first quarter to 4.5% the second quarter.  In addition, the vacancy rate has gone down slightly from 5.5% the first quarter to 5.1% for the second quarter and continues to remain high overall.  The increase in turnover and vacancy rates may be related to workload stress from increased intakes and investigations.

## Investigation and Service Delivery Performance - 2nd Quarter FY 2011

The following chart provides an overview of the APS In-Home program statewide performance indicators and benchmarks for the second quarter of FY 2011.  Overall the In-home program is continuing to grow substantially during the second quarter, with intakes 18.6% above the target (24,999 actual compared to 21,071 projected), completed investigations 16.1% above the target (20,357 compared to 17,541) and confirmed investigations 9.4% above the target (13,440 compared to 12,287), although confirmed investigations are 4.4% below the projected percentage.  The overall percentage of confirmed investigations has remained consistent over the first two quarters of FY 2011 ranging between 65.7% - 66%.  The average days for an investigation has risen from 45.7 days during the first quarter to 47.1 days in the second quarter while the average number of service delivery days has gone down from 34.2 days during the first quarter to 31 days during the second quarter.  The average daily caseload has gone down from 34.2 cases the first quarter to 31 days for the second quarter, reflecting the need to provide services more rapidly to keep up with the increase in intakes.

| Performance Indicators | FY 2010 Actual | FY 2011 Benchmarks | FY 2011 1st Qtr | FY 2011 2nd Qtr | FY 2011 3rd Qtr | FY 2011 4th Qtr | FY 2011 YTD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Average Hold Time Statewide Intake Phone Calls | 8.9 | 8.2 | 8.1 | 6.6 |  |  | 7.4 |
| Number of APS Reports of adult abuse/neglect/ exploitation | 103,361 | 84,285 | 26,273 | 24,999 |  |  | 51,272 |
| Number of Completed APS Investigations | 82,802 | 70,165 | 22,363 | 20,357 |  |  | 42,720 |
| Number (percent) of Confirmed APS Investigations | 56,053 (67.7%) | 49,417 (70.4%) | 14,684 (65.7%) | 13,440 (66.0%) |  |  | 28,124 (65.8%) |
| Average Days per Investigation Stage | 47.6 | 50 | 45.7 | 47.1 |  |  | 46.4 |
| Average Days per Service Delivery Stage | 50.9 | 60 | 44.9 | 45.4 |  |  | 45.2 |
| Average Daily Caseload per Worker | 33.1 | 39.2 | 34.2 | 31.0 |  |  | 32.6 |

## Employee Performance - 2nd Quarter FY 2011

The following chart provides an overview of employee performance indicators and benchmarks.  APS met or exceeded performance benchmarks for all of the investigation, risk assessment and delivery of protective services measures.  The two quality assurance scales - Investigation and Client Intervention - represent scores for nine and seven standards respectively and remain well above the benchmarks.

STATEWIDE INTAKE

| Performance Indicators | FY 2010 Actual | FY 2011 Benchmarks | FY 2011 1st Qtr | FY 2011 2nd Qtr | FY 2011 3rd Qtr | FY 2011 4th Qtr | FY 2011 YTD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Appropriately obtains and documents detailed information from reporters | 94% | 90-92% | 94.5% | 94.2% |  |  | 94.4% |
| Assesses and prioritizes reports of abuse/neglect accurately | 97.5 % | 90-92% | 97.4% | 97.3% |  |  | 97.4% |
| Accurately distributes reports, information and inquiries within timeframes | 98.5% | 92-94% | 99.7% | 99.3% |  |  | 99.5% |

INVESTIGATION

| Performance Indicators | FY 2010 Actual | FY 2011 Benchmarks | FY 2011 1st Qtr | FY 2011 2nd Qtr | FY 2011 3rd Qtr | FY 2011 4th Qtr | FY 2011 YTD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Percentage of cases initiated within 24 hours | 94.8% | 94-95% | 94.4% | 94.7% |  |  | 94.5% |
| Percentage of cases in which the initial client face-to-face visit occurred within the appropriate timeframe | 91.8% | 89-91% | 91.0% | 90.9% |  |  | 90.9% |
| Investigation Rating Scale | 90.7% | 80-86% | 91.1% | 89.9% |  |  | 90.5% |

RISK ASSESSMENT

| Performance Indicators | FY 2010 Actual | FY 2011 Benchmarks | FY 2011 1st Qtr | FY 2011 2nd Qtr | FY 2011 3rd Qtr | FY 2011 4th Qtr | FY 2011 YTD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Thoroughness of problem identification | 81.6% | 80-86% | 82.2% | 82.6% |  |  | 82.3% |
| Adequacy of supporting documentation | 92.8% | 80-86% | 94% | 93% |  |  | 93.4% |

DELIVERY OF PROTECTIVE SERVICES

| Performance Indicators | FY 2010 Actual | FY 2011 Benchmarks | FY 2011 1st Qtr | FY 2011 2nd Qtr | FY 2011 3rd Qtr | FY 2011 4th Qtr | FY 2011 YTD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Client Intervention Scale | 94.1% | 80-86% | 95.4% | 94% |  |  | 94.7% |

## Staffing - 2nd Quarter FY2011

The following chart provides information on the number of total FTEs, filled FTEs, and turnover rates.  These indicators provide regional and state office management with additional information to explain variations in performance.  During the second quarter of FY 2011, the In-Home caseworker turnover rate was 4.5% and 4.5% for supervisors.  Turnover in FY 2011 is at a slightly lower rate than in FY 2010.

IN-HOME CASEWORKERS

| Performance Indicators | FY 2010 Actual | FY 2011 1st Qtr | FY 2011 2nd Qtr | FY 2011 3rd Qtr | FY 2011 4th Qtr | FY 2011 YTD |
| --- | --- | --- | --- | --- | --- | --- |
| Year-to-Date Average Filled FTEs | 561.7 | 554.6 | 563.2 |  |  | 558.9 |
| Turnover | 18.1% | 3.6% | 4.5% |  |  | 8.1% |

IN-HOME SUPERVISORS

| Performance Indicators | FY 2010 Actual | FY 2011 1st Qtr | FY 2011 2nd Qtr | FY 2011 3rd Qtr | FY 2011 4th Qtr | FY 2011 YTD |
| --- | --- | --- | --- | --- | --- | --- |
| Year-to-Date Average Filled FTEs | 84.9 | 87.7 | 84.9 |  |  | 86.3 |
| Turnover | 7.0% | 0.0% | 4.5% |  |  | 4.5% |

ALL IN-HOME PROGRAMS

| Performance Indicators | FY 2010 Actual | FY 2011 1st Qtr | FY 2011 2nd Qtr | FY 2011 3rd Qtr | FY 2011 4th Qtr | FY 2011 YTD |
| --- | --- | --- | --- | --- | --- | --- |
| Total FTEs Appropriated | 890 | 890 | 890 |  |  | 890 |
| YTD Average FTEs Filled | 844 | 840.7 | 844.7 |  |  | 842.7 |
| Turnover | 15.0% | 3.0% | 3.9% |  |  | 6.9% |